## Gantt Chart
| Start Day Oct 23 | End Day: November 11
Task | Start (Day #) | Duration
Decide on the rules of Blokus and additional features | 0 | 2
Determine the objects and classes required to create Blokus | 2 | 3
Program tile generation | 5 | 3
Program the rules of Blokus | 6 | 6
Design a GUI for Blokus | 3 | 3
Implement a GUI for Blokus | 10 | 6
Testing and debugging our program by using test cases and customer input | 16 | 3
Commenting and documenting the program for possible future developers | 5 | 14